# CIVE 202

# Spring 2026

# Project 5

# Scope of Work

By Tessa Soukup, Ava Lavene, and Jamie Krab

Date submitted for review: February 27th, 2026

Submitted to: Civil and Environmental Engineering Department faculty

# Project Goals

The goal of this project is to analyze how access to drinking water in Sub-Saharan Africa has changed over time, using data from the WHO JMP database. This analysis is at the request of The Water Project, a non-governmental non-profit organization that works to provide access to potable water to communities across sub-Saharan Africa. The Water Project aims to improve sanitation, health, education, and food production through expanded access to clean water. We will need to produce time series plots for household water access, and a summary table comparing the differences in access between countries. These figures will then be evaluated to determine how water access has changed over time and we will conduct outside research to investigate why.

# Project Tasks

Task #1 – Download and Clean Data

First, the raw data will need to be downloaded from the JMP database for each country. The household drinking water access will then need to be isolated, and converted into a .csv file, in order to be imported to Python. This data can then be divided by household category, either rural or urban, such that the comparison between countries is more reliable. The .csv data will later be converted to Data Frames using the pandas package, in order to be plotted.

Task #2 – Data Plotting

Using tools like Matplotlib and Seaborn, we will graphically represent the water access data. After conversion to Data Frames, the data will be plotted in a lineplot, tracking the household water access in each household over time. We will use various plot arguments and formatting functions to create a legend and alter the dimensions of these graphs. We will also use a bar graph to analyze current water access levels across central African countries.

Task #3 – Data Analysis

We will compare data across the years to look for an increase in water access. Trends like rapidly increasing access or stagnations will be investigated. We will see if any economic, environmental, or civil events occurred which could have had an impact on water access initiatives like the Water Project. R squared values can be used to determine the severity with which the change is occurring. All observations will be described or quantified in the final written report.

# Deliverables

After the completion of these tasks, the following items will be sent to the client: The Water Project.

| Deliverable | Files Included | Due to Client by |
| --- | --- | --- |
| Raw Excel Data | CIVE202_Spring2025_Project5_RawExcelData.xlsx | 5/8/2026 |
| Gantt Chart | CIVE202_Spring2025_Project5_GanttChart.xlsx | 5/8/2026 |
| Python Code | CIVE202_Spring2025_Project5_PythonCode.docx | 5/8/2026 |
| Annotated Code Document | CIVE202_Spring2026_Project5_AnnotatedCodeDocument.docx | 5/8/2026 |
| Scope of Work | CIVE202_Spring2025_Project5_ScopeOfWork.docx | 5/8/2026 |
| Written Report | CIVE202_Spring2026_Project5_WrittenReport.docx | 5/8/2026 |