## Sheet1
Project #3 - GANTT CHART
PROJECT TITLE |  | CIVE 202 PROJECT #3 |  |  |  |  | COMPANY NAME | [6 empty] | Group INFRA-1-16
PROJECT MANAGER |  | Jamie Krab, Ava Lavene, Tessa Soukup |  |  |  |  | START DATE | [6 empty] | 2026-03-05
[7 empty] | END DATE | [6 empty] | 2026-03-27
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE
[7 empty] | WEEK 1 (3/02-3/05) |  |  |  |  | WEEK 2 (3/09-3/13) |  |  |  |  | WEEK 3 (3/16-3/20) |  |  |  |  | WEEK 4 (3/23-3/27) |  |  |  |  | WEEK 5 (3/30-4/03) |  |  |  |  | WEEK 6 (4/06-4/10)
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Data Processing
1.1 | Create Gantt Chart | All | 2026-02-26 | 2026-02-27 | 1 | 100% | bar: WEEK 1 (3/02-3/05) M to WEEK 1 (3/02-3/05) F; WEEK 4 (3/23-3/27) M to WEEK 4 (3/23-3/27) F; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
1.1.1 | Read and Understand Client Prompt | All | 2026-02-26 | 2026-02-27 | 1 | 40% | bar: WEEK 1 (3/02-3/05) M to WEEK 1 (3/02-3/05) F; WEEK 4 (3/23-3/27) M to WEEK 4 (3/23-3/27) F; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
1.2 | Complete Additional Necessary Research | All | 2026-02-26 | 2026-02-27 | 1 | 10% | bar: WEEK 1 (3/02-3/05) M to WEEK 1 (3/02-3/05) F; WEEK 4 (3/23-3/27) M to WEEK 4 (3/23-3/27) F; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
2 | Scope of Work
2.1 | Write Project Goals | Jamie K | 2026-02-27 | 2026-03-06 | 3 | 0% | bar: WEEK 1 (3/02-3/05) T to WEEK 1 (3/02-3/05) F; WEEK 4 (3/23-3/27) M to WEEK 4 (3/23-3/27) F; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
2.2 | Write Project Tasks | Ava L | 2026-02-27 | 2026-03-06 | 3 | 100% | bar: WEEK 1 (3/02-3/05) T to WEEK 1 (3/02-3/05) F; WEEK 4 (3/23-3/27) M to WEEK 4 (3/23-3/27) F; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
2.3 | Write Project Deliverables | Tessa S | 2026-02-27 | 2026-03-06 | 3 | 0% | bar: WEEK 1 (3/02-3/05) T to WEEK 1 (3/02-3/05) F; WEEK 4 (3/23-3/27) M to WEEK 4 (3/23-3/27) F; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
2.4 | Finialize SOW | All | 2026-02-27 | 2026-03-06 | 4 | 0% | bar: WEEK 1 (3/02-3/05) T to WEEK 1 (3/02-3/05) F; WEEK 4 (3/23-3/27) M to WEEK 4 (3/23-3/27) F; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
3 | Flow Diagram
3.1 | Create Diagram | Tessa S | 2026-03-06 | 2026-03-12 | 6 | 100% | bar: WEEK 2 (3/09-3/13) M to WEEK 2 (3/09-3/13) F; WEEK 4 (3/23-3/27) M to WEEK 4 (3/23-3/27) F; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
4 | Draft Methods
| Write methods section | Jamie K | bar: WEEK 4 (3/23-3/27) M to WEEK 4 (3/23-3/27) F; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
4 | Python Code
4.1 | Clean Data in excel | All | 2026-02-27 | 2026-02-27 | 0 | 100% | bar: WEEK 1 (3/02-3/05) M to WEEK 1 (3/02-3/05) F; WEEK 4 (3/23-3/27) M to WEEK 4 (3/23-3/27) F; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
4.2 | Organize data in python | All | 2026-03-08 | 2026-03-12 | 4 | 0% | bar: WEEK 2 (3/09-3/13) M to WEEK 2 (3/09-3/13) F; WEEK 4 (3/23-3/27) M to WEEK 4 (3/23-3/27) F; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
4.3 | create comparison table | Jamie K | 2026-03-08 | 2026-03-13 | 5 | 0% | bar: WEEK 3 (3/16-3/20) M to WEEK 4 (3/23-3/27) F; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
4.4 | create time series plot | Tessa S | 2026-03-13 | 2026-03-20 | 7 | 100% | bar: WEEK 3 (3/16-3/20) M to WEEK 4 (3/23-3/27) F; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
4.4 | Work on final code | All | 2026-03-13 | 2026-03-19 | 6 | 100% | bar: WEEK 4 (3/23-3/27) M to WEEK 5 (3/30-4/03) W; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
5 | Written Report
5.1 | Write Introduction/Background of Technical Report | Ava L | 2026-03-12 | 2026-03-19 | 7 | 0% | bar: WEEK 2 (3/09-3/13) M to WEEK 2 (3/09-3/13) F; WEEK 4 (3/23-3/27) M to WEEK 4 (3/23-3/27) F; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
5.2 | Write Methods (Excel to Python traslation and parameters) of Technical Report | Jamie K | 2026-03-12 | 2026-03-19 | 7 | 0% | bar: WEEK 3 (3/16-3/20) M to WEEK 4 (3/23-3/27) F; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
5.3 | Write Results/Discussion of Technical Report | Ava L | 2026-03-12 | 2026-03-20 | 8 | 100% | bar: WEEK 4 (3/23-3/27) M to WEEK 5 (3/30-4/03) T; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
5.4 | Write Reference List of Technical Report | All | 2026-03-20 | 2026-03-20 | 0 | 100% | bar: WEEK 4 (3/23-3/27) M to WEEK 5 (3/30-4/03) T; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
6 | Annotated Code Document
6.1 | Review the finished Python Code | All | 2026-03-06 | 2026-03-19 | 13 | 0% | bar: WEEK 4 (3/23-3/27) M to WEEK 5 (3/30-4/03) T; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
6.3 | Complete the Annontated Code Document | Jamie K | 2026-03-17 | 2026-03-19 | 2 | 100% | bar: WEEK 4 (3/23-3/27) M to WEEK 5 (3/30-4/03) T; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
7 | Final Project
7.1 | Put all documents and links into GitHub including the code, data, and a README file | All | 2026-03-20 | 2026-03-23 | 3 | 0% | bar: WEEK 4 (3/23-3/27) M to WEEK 5 (3/30-4/03) W; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F
7.2 | Reflection Quiz | All | 2026-03-20 | 2026-03-23 | 3 | 0% | bar: WEEK 4 (3/23-3/27) M to WEEK 5 (3/30-4/03) W; WEEK 6 (4/06-4/10) M to WEEK 6 (4/06-4/10) F